## Sheet1
| Module | Task | Issues Encountered
23-05-2022 to 27-05-2022 |  | 23-05-2022 to 27-05-2022
Venkatesh | Jobseeker | Worked on testing the jobseeker module and need to fix the bugs
| Employer | Worked on testing the Employer module
| python backend | Worked on deploying the codes in gpu server
| Corporate Trainer | Worked on testing the corporate trainer
Hemanth Muangala | Jobseeker | Worked on resolving issues in job recommendations
Worked on creating job to delete jobs from elasticsearch
Worked on issue regarding video analysis out of memory issue
Narayana | Jobseeker | Worked on testing the jobseeker module and resolved the bugs
| Employer | Worked on testing the Employer module resolved the bugs
| Corporate Training | Worked on testing the Corporate Training module
Nagoor | Employer | Worked on testing total employer flow and resolved the bugs
| Jobseeker | Bug fixing in Jobseeker module
| Corporate Training | Testing corporate trainer and resolving the bugs
Saiteja | Employer | Worked on testing the total Employer module resolved the bugs
| Corporate Training | Worked on testing the Corporate Training module
| Jobseeker | Worked on testing the Jobseeker module
Siva Sai | Jobseeker | Job seeker length validations
Documenting the authorities and bug fixing on job seeker
| PlatformUser | bug fixing on platform user grid
| PlatformUser | Bug Fixing on platform user module
Testing employer and job seeker bug fixing
Sivani | Corporate and Employer | Corporate Trainer and Employer length validations
Documenting all the authorities and bug fixing
Documenting all the authorities and bug fixing on field validations
working on deployment diagram
Testing employer and employer bug fixing
Kiran Kothinti | Discovery Platform | Event management api code changes
| Skill details | bug fixing on field validations
Event management api's testing
Discovery platform api testing on events
Employer testing and code checking
Karishma | Jobseeker | changes in jobseeker registration page
| Employer | worked on posted jobs(data collection)
| Jobseeker | Jobseeker on testing the jobseeker module
Jobseeker on testing the Jobseeker module
| Employer | Jobseeker on testing the Employer module
Shannu |  | bug fixings from sheet
bug fixings from sheet
Api response needed to checked and update according to it
Api response needed to checked and update according to it
Employee code checking and testing entire module
sathyendra | Jobseeker | worked on testing entire jobseeker Module
| Employer | worked on testing the Employer module
| Individual Trainer | worked on testing individual trainer for a profile switch user
Ragini Gone | Jobseeker | worked on testing the jobseeker module from registration
| Employer | Worked on testing Employer module
worked on testing the jobs crawler for updated jobs using deltafetch plugin
Manasa | Employer | Worked on Retesting Employer with fixed issues
Worked on Testing Corporate trainer , Individual trainer user profile and wrote the checklist for Corporate Trainer
Worked onTesting jobseeker userprofile
Worked on Testing corporate trainer and jobseeker field validations
Wrote the Individual Trainer and Employer Checklist Testcases
Shashi | Employer | List of jobseekers recommeded to employer for the perticular job api integration.
Employer module flow testing and bug fixes.(JP-138,JP-141 )
Employer registration api integration for duplicte entries while registration.
Rajesh | Employer | Employer Testing along with fixed issues
| Individual Trainer | Individual Trainer and Jobseeker modules UI testing
| Jobseeker | Job seeker field validation testing
Employer and Jobseeker testing
Jyothi | Job Seeker | Tested Jobseeker Dashboard (Job and Course Recommendations and Search)
| Individual Trainer | Tested overall flow
| Employer | Tested overall flow
| Platform User | Retesting of platform user API changes (approve, reject)
Mamatha | Job Seeker | Tested and Retested entire Jobseeker Module
| Individual Trainer | Tested and Retested entire Trainer Module
| Employer | Tested and Retested entire Employer Module
| Corporate Trainer | Tested and Retested entire Corporate Trainer Module
| Platform User | Tested and Retested entire Platform Module
Divya | Job Seeker | Fixing the bugs in applied jobs,saved jobs, and WishList
| Job Seeker | Worked on suggestions given by testers and solved encoding issue in applied jobs and saved jobs
| Individual Trainer | Worked on suggestions given by testers and solved encoding issue in applied jobs and saved jobs(JP-138,JP-141 )
| Individual Trainer | Worked on delete buttons Api integration in course section and course content
30-05-2022 to 03-06-2022
Hemanth Muangala | Trainer | Worked on issue regarding video analysis out of memory issue and resolved it
Worked on testing application and raised bugs.
Worked on retesting the application on fixed bugs and closed them.
Venkatesh | Jobseeker | Worked on testing the Jobseeker JP-189,191,249,191
Worked on issues in issue tracker JP-221,231,245,249,264,265,272
| Employer | Worked on testing the Employer JP-245
Lakshmi Narayana | Jobseker | worked on Testing JobSeeker Module and raised bugs
worked on issues in issue tracker
Worked on retesting the application on fixed bugs and closed them.
Shashi | Issues | Issues fixed JP-166 , JP-165, JP-208, JP-004, JP-118
Duplicate company name get call api integration for employer
Saiteja | Employer | Worked on Retesting the total Employer module resolved the bugs
Worked on modifying the Employer user profile and details screens
Issues fixed JP-193, JP-200, JP-204, JP-226, JP-239, JP-261, JP-263, JP-216
Mamatha |  | Tested and Retested Employer and Jobseeker
Corporate and Course assessment testing
Tested Individual Training and Jobseeker modules
Manasa |  | Worked on Retesting the employer and closed the fixed issues
Worked on Retesting the Jobsseeker and closed the fixed issues
Worked on Retesting Individual Training and closed fixed issues
Rajesh | jobseeker | Retested the Jobsseeker on fixed issues
Retesting the Corporate Trainer
Retesting the application and close fixed issues
Jyothi | Job Seeker | Tested overall flow
| Individual Trainer | Tested overall flow
| Employer | Tested overall flow
| Corporate Trainer | Tested overall flow
| Platform User | Tested overall flow
Nagoor | Issues | Issues Fixed JP-256, JP-241, JP-238, JP-234, JP-232, JP-227, JP-224, JP-218, JP-196, JP-194, JP-191, JP-189
Sivani | Employer | fixed all the bugs JP-273,JP-242,JP-166,JP-146,JP-142,
| Jobseeker | tested jobseeker flow
Fixed all the Response messages.
siva sai | Jobseeker | in jobseker save jobs not working
In jobseeker registration,technical skills field is accepting same skills twice.
In jobseeker apply job is not working
In applied jobs location field is empty
Kiran Kothinti | Employer | Bugs fixed in employer and profile questons JP-174,JP-204,JP-206,JP-276
Platform user module flow was tested
sucees message modifications as per suggestions
Karishma | Training | fixed all the bugs JP-065,JP-252,JP-255
Jobseeker Test flow
master data management
Shannu | Training | fixed all bugs JP-80, JP-161, JP-201, JP-231, JP-252
Jobseeker Test flow
weekly recomendation mail scheduler
Mounika | Jobseeker | Course feedback , Dates validation in education
| Individual Training | Course Completion
| Bugs | JP-205, JP-247, JP- 267
Divya | Corporate Training | Added user profile tab to the corporate trainer and given validation to the duplicate company
| Individual Training | Worked on section order no issue in section

## Sheet2
Name Of the Resource | Week ( 23-05-2022 to 27-05-2022) | Week ( 30-05-2022 to 03-06-2022)
Venkatesh | • Worked on testing the jobseeker module and fixed bugs ( User profile validations ). • Worked on testing the jobseeker module and fixed bugs ( User profile validations ). • Worked on testing the Employer module • Worked on deploying the codes in gpu server • Worked on testing the corporate trainer | • Worked on testing the Jobseeker and raised issues JP-189,191,249,191 • Worked on issues in issue tracker JP-221,231,245,249,264,265,272 • Worked on testing the Employer JP-245
Hemanth Muangala | • Worked on resolving issues in job recommendations • Worked on creating job to delete jobs from elasticsearch • Worked on issue regarding video analysis out of memory issue | • Worked on issue regarding video analysis out of memory issue and resolved it • Worked on testing application and raised bugs. • Worked on retesting the application on fixed bugs and closed them.
Narayana | • Worked on testing the jobseeker module and resolved the bugs • Worked on testing the Employer module resolved the bugs • Worked on testing the Corporate Training module | • worked on Testing JobSeeker Module and raised bugs • worked on issues in issue tracker • Worked on retesting the application on fixed bugs and closed them.
Nagoor | •Worked on testing total employer flow and resolved the bugs •Bug fixing in Jobseeker module •Testing corporate trainer and resolving the bugs | • "Issues Fixed JP-256, JP-241, JP-238, JP-234, JP-232, JP-227, JP-224, JP-218, JP-196, JP-194, JP-191, JP-189"
Saiteja | • Worked on testing the total Employer module resolved the bugs • Worked on testing the Corporate Training module • Worked on testing the Jobseeker module | •Worked on Retesting the total Employer module resolved the bugs •Worked on modifying the Employer user profile and details screens •Issues fixed JP-193, JP-200, JP-204, JP-226, JP-239, JP-261, JP-263, JP-216
Siva Sai | •Job seeker length validations •Documenting the authorities and bug fixing on job seeker •bug fixing on platform user grid •Bug Fixing on platform user module •Testing employer and job seeker bug fixing | •in jobseker save jobs not working •In jobseeker registration,technical skills field is accepting same skills twice. •In jobseeker apply job is not working •In applied jobs location field is empty
Kiran Kothinti | •Event management api code changes •bug fixing on field validations •Event management api's testing •Discovery platform api testing on events •Employer testing and code checking | •Bugs fixed in employer and profile questons JP-174,JP-204,JP-206,JP-276 •Platform user module flow was tested •sucees message modifications as per suggestions
Karishma | •changes in jobseeker registration page •worked on posted jobs(data collection) •Jobseeker on testing the jobseeker module •Jobseeker on testing the Jobseeker module •Jobseeker on testing the Employer module | •fixed all the bugs JP-065,JP-252,JP-255 •Jobseeker Test flow •master data management
Shannu | •bug fixings from sheet •bug fixings from sheet •Api response needed to checked and update according to it •Api response needed to checked and update according to it •Employee code checking and testing entire module | •fixed all bugs JP-80, JP-161, JP-201, JP-231, JP-252 •Jobseeker Test flow •weekly recomendation mail scheduler
sathyendra | •worked on testing entire jobseeker Module •worked on testing the Employer module •worked on testing individual trainer for a profile switch user | • worked on pagenation in Employer dashboard • worked on resolving the issues in issue tracker •worked on testing the job seeker module
Ragini Gone | •worked on testing the jobseeker module from registration •Worked on testing Employer module •worked on testing the jobs crawler for updated jobs using deltafetch plugin | •worked on testing the Employer module • worked on testing the Individual Trainer module • KT session on git and jobs crawler deltafetch plugin • worked on closing the issues
Manasa | •Worked on Retesting Employer with fixed issues •"Worked on Testing Corporate trainer , Individual trainer user profile and •wrote the checklist for Corporate Trainer" •Worked onTesting jobseeker userprofile •Worked on Testing corporate trainer and jobseeker field validations •Wrote the Individual Trainer and Employer Checklist Testcases | •Worked on Retesting the employer and closed the fixed issues •Worked on Retesting the Jobsseeker and closed the fixed issues •Worked on Retesting Individual Training and closed fixed issues
Shashi | •List of jobseekers recommeded to employer for the perticular job api integration. •Employer module flow testing and bug fixes.(JP-138,JP-141 ) •Employer registration api integration for duplicte entries while registration. | •Issues fixed JP-166 , JP-165, JP-208, JP-004, JP-118 •Duplicate company name get call api integration for employer
Rajesh | •Employer Testing along with fixed issues •Individual Trainer and Jobseeker modules UI testing •Job seeker field validation testing •Employer and Jobseeker testing | •Retested the Jobseeker on fixed issues •Retesting the Corporate Trainer •Retesting the application and close fixed issues •Retesting the application and close fixed issues
Jyothi | •Tested Jobseeker Dashboard (Job and Course Recommendations and Search) •Tested overall flow •Tested overall flow •Retesting of platform user API changes (approve, reject) | •Tested overall flow •Tested overall flow •Tested overall flow •Tested overall flow •Tested overall flow
Mamatha | •Tested and Retested entire Jobseeker Module •Tested and Retested entire Trainer Module •Tested and Retested entire Employer Module •Tested and Retested entire Corporate Trainer Module •Tested and Retested entire Platform Module | •Tested and Retested Employer and Jobseeker •Corporate and Course assessment testing •Tested Individual Training and Jobseeker modules
Divya | •Fixing the bugs in applied jobs,saved jobs, and WishList •Worked on suggestions given by testers and solved encoding issue in applied jobs and saved jobs •Worked on suggestions given by testers and solved encoding issue in applied jobs and saved jobs(JP-138,JP-141 ) •Worked on delete buttons Api integration in course section and course content | •Added user profile tab to the corporate trainer and given validation to the duplicate company •Worked on section order no issue in section
Sivani | •Corporate Trainer and Employer length validations •Documenting all the authorities and bug fixing •Documenting all the authorities and bug fixing on field validations •working on deployment diagram •Testing employer and employer bug fixing | •fixed all the bugs JP-273,JP-242,JP-166,JP-146,JP-142, •Tested jobseeker flow •Fixed all the Response messages.
Mounika | • Worked on integrating approved courses, rejected courses in platform user. • Worked on Course completion assessment and intermediate assessment in course creation •Worked on fixing bugs. | •Course feedback , Dates validation in education •Course Completion •JP-205, JP-247, JP- 267